## BARK Implementation Checklist
Implementation Checklist
|  | ITEM | CATEGORY | RESPONSIBLE | DUE DATE | COMPLETE | NOTES | TUTORIALS
|  | Create an action plan | Pre-implementation |  |  | 1 | This Checklist forms the bulk of Plan
|  | Nominate your BARK "Top Dog" | Pre-implementation |  |  |  | To make decisions and authorise customisation
|  | Gather & Tidy existing bulk data for importing (clients, suppliers, inventory, staff etc) | Pre-implementation |  |  |  | BARK allows import to ANY table
|  | Provide Admin access to BSD Developers existing systems to link to | Integration |  |  |  | We can integrate nearly any system
| How to use this checklist | Provide Admin access to BSD Developers to Set up accounting integration link | Integration |  |  |  | add us as a user to Myob etc and we'll take care of it
|  | Import Customers (unless integrating with accounting / other system) | Integration / Pre-implementation |  |  |  | if you are not integrating, then import from excel etc
|  | Import Accounts (unless integrating with accounting / other system) | Integration / Pre-implementation |  |  |  | if you are not integrating, then import from excel etc
|  | Import Suppliers (unless integrating with accounting / other system) | Integration / Pre-implementation |  |  |  | if you are not integrating, then import from excel etc
|  | Import Staff (unless integrating with accounting / other system) | Integration / Pre-implementation |  |  |  | if you are not integrating, then import from excel etc
|  | Import Products (unless integrating with accounting / other system) | Integration / Pre-implementation |  |  |  | if you are not integrating, then import from excel etc
|  | Import Assets (unless integrating with accounting / other system) | Integration / Pre-implementation |  |  |  | if you are not integrating, then import from excel etc
|  | Provide Admin access to public website (if not hosting with BSD) to link chat and forms | Integration |  |  |  | get 24/7 chat and leads to sms from your public site
| 2.273% | Confirm your Organisation Details | Site Admin
|  | Set up Business Units / User GROUPS | Site Admin |  |  |  | BARK tabs can suit your Departments
|  | Set User Access | Site Admin |  |  |  | as many groups as you like each with different access and pages
|  | Select a color scheme, upload logo and any icon changes | Customisation |  |  |  | you make the site look how you want, all images are yours to swap
|  | Set up Locations and Managers / Contacts | Site Admin |  |  |  | for 1 or 100 offices around the globe
|  | Send through custom / existing field forms | Site Admin |  |  |  | we can make your own custom field forms overnight
|  | Set up Payrates | Site Admin |  |  |  | upload award or set payrates
Packed |  | Set up work types | Site Admin |  |  |  | label all your service offerings
|  | Set up default settings for Pricing and Conditions, Times etc | Site Admin |  |  |  | defaults speed up the quoting process
|  | Set or Import the Standard Weekly Timesheet | Site Admin |  |  |  | upload or enter your standard weekly hours
|  | Set or Import the Standard Weekly Jobs | Site Admin |  |  |  | upload or enter your standard weekly jobs
|  | Upload Induction Materials and Q&A | Site Admin |  |  |  | BARK is your online training school
|  | Upload Training Materials and Q&A | Site Admin |  |  |  | BARK is your online training school
|  | Upload Co Licenses, Insurance and Certificates | Site Admin |  |  |  | BARK is your online certificate repository with reminders
|  | Set SMS/ Email Conditions Defaults | Site Admin |  |  |  | you decide what gets emailed/sms to whom & when
|  | Set up BARK_APP including GPS tracking (optional) | Site Admin |  |  |  | if you are using the BARK app, customise this
|  | Using Report Builder - Create Custom Reports | Customisation |  |  |  | Job Reports etc can be pdf and emailed
|  | Train Admin staff | Training |  |  |  | Online Training, Video Tutorials and Documentation available
|  | Train Finance staff | Training |  |  |  | Online Training, Video Tutorials and Documentation available
|  | Train Operations staff | Training |  |  |  | Online Training, Video Tutorials and Documentation available
|  | Train Sales and Marketing staff | Training |  |  |  | Online Training, Video Tutorials and Documentation available
|  | Train Field Workers | Training |  |  |  | Online Training, Video Tutorials and Documentation available
|  | Set Business Goals, Objectives and Tasks | Site Admin |  |  |  | Managers can sign on to tasks
|  | Set up Call and Chat Types Q&A | Site Admin |  |  |  | Put your FAQs to give chatters the answers they need
|  | Decide on Sign On For Duty custom requirements | Customisation |  |  |  | do your field workers take Vehicles, Keys or Equipment?
|  | Decide on SWMS / Risk Assessment / Induction custom requirements | Customisation |  |  |  | Each job can have SWMS or Induction check before work
|  | Customise co/staff and supplier certification requirements | Customisation |  |  |  | Which licenses or certs are relevant to your organisation?
|  | Customise invoice, email and layouts | Customisation |  |  |  | Invoices are sleek and modern with your logos etc
|  | Customise quote form, email and layouts | Customisation |  |  |  | From a single purchase to major works projects all on your phone
|  | Customise Customer Satisfaction surveys, email and forms | Customisation |  |  |  | Make it easy for customers to give you feedback you need
|  | Set up or Customise Customer Meeting form and reports | Site Admin |  |  |  | Design your own customer meeting forms and reports
|  | Set up sales phases and forecast | Site Admin |  |  |  | Sales team can work accountably from their mobile
This checklist is designed to help you plan and keep track of key implementation activities.
Feel free to edit, delete or add new items.
Change any 'Complete' cell to 1 (one) for a green tick, or 0 (zero) for no tick.
Click the tutorial icons to Start an online tutorial Watch a video tutorial Read a help page